## Sheet1
Date | Start Time | End Time | Total Hours | Task
2021-08-12 | 14:00 | 18:30 | 4hr 30min | * Formatted the code with 4 spaces indent * Converted the code from python 2.x to 3.x using 2to3 library * Migrated Numeric to numpy * Migrated EpicsCA, EpicsMotor to epics * Removed unwanted \ and semicolon * removed math dependency * Refactored the code to remove * imports In-Progress * Learning basics of epics library * Exploring the Alternative of `FileBrowse`
2021-08-13 | 2:00 | 18:00 | 4hr 00min | * Explored the alternative of FileBrowse * Migrated the FileBrowse library to tkinter.filedialog.askopenfile * Migrated the String library to str * Setup EPICS in local machine * Tried running the app in python 2.7 environment In-Progress * Learning basics of epics and tkinter (GUI) libraries
2021-08-16 | 10:00 | 13:00 | 7hr 00min | * Handled the PV connection status errors * Started Working on Task 2 * Setup musclex project in my local system * Running musclex * Going through the musclex Documentation In-Progress * Analyse the code for Task 2.1
| 14:00 | 6:00
2021-08-17 | 10:00 | 13:00 | 7hr 00min | * Fixed the File read exception while Saving Parameter * Completed Task 2.1
| 14:00 | 6:00
2021-08-18 | 9:00 | 13:00 | 8hr 00min | * Setup code in BioCAT machine * Updated Table, Epic module methods to support Python 3 * Run and test the code in BioCAT Environment In-Progress * Task 2.2
| 14:00 | 6:00
2021-08-19 | 10:00 | 13:00 | 8hr 00min | * Analyse the issue related to motor movement * Incorporate the Log file parsing logic into existing Functionality In-Progress * Task 2.2
| 14:00 | 7:00
2021-08-20 | 10:00 | 13:00 | 8hr 00min | * Debugging the issue related to HeatMap click function In-Progress * Task 2.2 * Read multiple Log files
| 14:00 | 19:00
2021-08-23 | 2:00 | 18:00 | 4hr 00min | * created the log file dataset * Changed the DI to support Single Log files In-Porgress * Task 2.2
2021-08-24 | 2:00 | 18:00 | 4hr 00min | * Made changes to support multiple log files In-Porgress: * Task 2.2
2021-08-25 | 2:00 | 16:00 | 2hr 00min | * Created the dataset and tested the DI program for multiple log files Complete: * Task 2.2
2021-08-26 | - | - | 0hr 00min
2021-08-27 | 4:00 | 20:00 | 4hr 00min | Pushed the changes to support log files in DI program Debugging the epic motor movement issue
2021-08-28 | 26:00 | 42:00 | 4hr 00min | Debugging the epic motor movement issue